## Sheet1
ID | Task | Start Day | Duration
A1 | Review slides and assignment | 1 | 1
A2 | Finalize user stories and acceptance criteria | 1 | 2
A3 | Write scope and constraints | 2 | 1
A4 | Design data model | 2 | 1
A5 | Plan function signatures | 3 | 1
A6 | Code add stock | 3 | 1
A7 | Code add bond | 4 | 1
A8 | Code make summary | 4 | 1
A9 | Code make text report | 5 | 1
A10 | Demo script | 5 | 1
A11 | Valid input tests | 6 | 1
A12 | Invalid input tests | 6 | 1
A13 | Save sample run and output | 7 | 1
A14 | Update README | 7 | 1
A15 | Update SRS | 8 | 1
A16 | Update Week 1 log | 8 | 1
A17 | Schedule check and buffer | 9 | 1
A18 | Package submission | 9 | 1
Buffer | Buffer time | 6 | 1